## General information
Project Name | ASearch - find info of LOL EU | Description | Find information of user in LOL at server eu (have permission
Author | Tan, To The
Period | 1 month | Start date | 14 May, 2017 | End date | 14 June, 2017
Enviroment | Detail
Java | 1.8
Database | MySql
IDE | eclipse neon, workbench 6..3
Spring boot
Spring security
AngularJs
Cache | ehcache

## Plan
4 sprint
Sprint 1 | 15 | 21
Sprint 2 | 22 | 28
Sprint 3 | 29 | 4
Sprint 4 | 5 | 11
Backlog
Find information of user
Register account for advenced feature (Analysis)
Analysis information of user when play game
Statistic
to be continue...

## Sprint 1
Sprint 1 |  | Status
init project and integrate spring security, angularjs | 1 days | New | AS-0001
research LOL API | 1 days | New | AS-0002
design and implement database | 1 days | New | AS-0003
design and implement API (integrate with LOL API) | 1 days | New | AS-0004
design and implement UI (common) | 3 days | New | AS-0005